## Task
Name | Module | Task | Status
Shashwat | User Login/Signup | Create web page for user login | Pending
|  | Create web page for user signup | Pending
|  | Connect with backend | Pending
|  | CRUD operation with mysql | Pending
Jyoti | Upload Excel files | Create a web page to upload files(max 5 files) | Pending
|  | Validate the files | Pending
|  | Import files into MySql DB | Pending
Chirag | Check duplicate data | Check duplicate rows of table | Completed
|  | Return the statistics about duplicate rows for creating charts | Completed
Shiv | Grouping data | Create web page for grouping data functionality | Completed
|  | Group the table based on selected columns in backend | Completed
| #doubt | import newly generated grouped table into mysql | Pending
Saketha | Chart data monitor(Visualization) | Create web page for dashboard | Completed
|  | Generate charts for the tables | Working
|  | Show charts in the dashboard | Completed

## Doubts
Sr. No. | Doubt | Solution
1 | What to do in grouping data? | Create a new table from the original table by grouping selected columns from it and import newly created table into mySql DB.
2 | What to do in duplicate data? | Check duplicate rows from the table. Return the statistics for all the original tables
3 | Which kind of charts we have to show? | Create charts for the statistics about the data. Like, how many duplicate rows in each files, how many rows and columns are there in the tables etc.
4 | Do we need user login/signup? | As per your convenience.